## GanttChart
Vital link | Project Start Date | 2025-11-17 |  |  |  | Display Week
[7 empty] | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
[9 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05
 | time axis 2025-11-17 to 2026-01-11
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-11-17 to 2026-01-11
1 | Networking tasks | Akash | Ryan
1.1 | BLE course |  |  | 2025-11-17 | 2025-12-08 | 22 | 4.545e-06% | 1e-06
1.2 | Test 1 Basic functionality - send 1KHz sin wave to hub
1.2.1 | Initiate basic connection to node |  |  | 2025-12-15 | 2025-12-25 | 11 | 9.091e-06% | 1e-06
1.2.2 | Rx data continuously |  |  | 2025-12-25 | 2026-01-04 | 11 | 9.091e-06% | 1e-06
1.3 | Test 2: Advanced functionality
1.3.1 | Real time Rx from 3+ nodes, with continuous graphs on all 3-10 nodes |  |  | 2026-01-05 | 2026-01-18 | 14 | 7.143e-06% | 1e-06
1.3.2 | Design and implement Adjust settings/behaviour on nodes |  |  | 2026-01-05 | 2026-01-25 | 21 | 4.762e-06% | 1e-06
1.3.2.1 | add/remove nodes |  |  | 2026-01-05 | 2026-01-12 | 8 | 1.25e-05% | 1e-06
1.3.2.2 | change samplingRates |  |  | 2026-01-12 | 2026-01-19 | 8 | 1.25e-05% | 1e-06
1.3.2.3 | ect behaviours depending on sensors |  |  | 2026-01-19 | 2026-01-26 | 8 | 1.25e-05% | 1e-06
1.4 | Test 3: Data Export | [6 empty] | 0
1.4.1 | Have the ability to upload data throughout the day on a set of sensors. |  |  | 2026-02-03 | 2026-02-23 | 21 | 4.762e-06% | 1e-06
2 | HUB/GUI ( turn data into actionable feedback) | Akash | Ryan
2.1 | Research and talk people in industry to better understand how our product can best help them help patients. |  |  | 2025-11-17 | 2025-12-01 | 15 | 6.667e-06% | 1e-06
2.2 | Derived Metrics Dashboard: Real-time visualization of "3-5" sensors (bobs request) |  |  | 2026-01-05 | 2026-01-11 | 7 | 1.429e-05% | 1e-06
2.3 | Node Management Interface
2.3.1 | Enable, disable, connect, disconnect, battery life |  |  | 2025-12-15 | 2026-01-05 | 22 | 4.545e-06% | 1e-06
2.3.2 | Options to change behaviour of sensors. sampling rate, filtering, additional behaviour of sensors, alert thresh-holds |  |  | 2025-12-15 | 2026-01-05 | 22 | 4.545e-06% | 1e-06
2.4 | Upload mode
2.4.1 | upload data from sensors onto hub |  |  | 2025-12-15 | 2026-01-05 | 22 | 4.545e-06% | 1e-06
2.5 | Derive usable metrics
2.5.1 | Derive heart-rate from PPG signals |  |  | 2026-02-13 | 2026-02-26 | 14 | 7.143e-06% | 1e-06
2.5.2 | Derive heart-rate from ECG signals |  |  | 2026-02-26 | 2026-03-11 | 14 | 7.143e-06% | 1e-06
2.5.3 | Calculate respiratory rate from ECG |  |  | 2026-02-26 | 2026-03-11 | 14 | 7.143e-06% | 1e-06
2.5.4 | Estimate blood pressure from ECG+PPG timing (trend-based). |  |  | 2026-02-26 | 2026-03-11 | 14 | 7.143e-06% | 1e-06
3 | Node firmware/sensors | Parry | Akash
3.1 |  |  |  | 2022-11-17 | 2022-11-17 | 1 | 0% | 0
3.2 | Nordic SDK COURSE |  |  | 2025-11-17 | 2025-12-08 | 22 | 9.091% | 2
3.3 | Accept basic connection |  |  | 2025-12-15 | 2026-01-05 | 22 | 0% | 0
3.4 | Tx data continously |  |  | 2025-12-15 | 2026-01-05 | 22 | 4.545e-06% | 1e-06
3.5 | Tx data with proper ID system |  |  | 2026-01-05 | 2026-01-18 | 14 | 7.143e-06% | 1e-06
3.6 | Code temperature sensor |  |  | 2026-01-18 | 2026-01-31 | 14 | 7.143e-06% | 1e-06
3.7 | Code PPG sensor |  |  | 2026-01-31 | 2026-02-13 | 14 | 7.143e-06% | 1e-06
3.8 | Code ECG sensor |  |  | 2026-02-13 | 2026-02-26 | 14 | 7.143e-06% | 1e-06
4 | Mechanical design( ensure signals can be properly measured) | Jishiv | Ryan
4.1 | Design and think about Ideal form-factors for sensors |  |  | 2025-11-17 | 2025-12-16 | 30 | 3.333e-06% | 1e-06
4.2 | Temperature(Side of the Chest (High accuracy for medical-grade)) |  |  | 2026-01-18 | 2026-01-31 | 14 | 7.143e-06% | 1e-06
4.3 | PPG(underside of wrist) |  |  | 2026-01-31 | 2026-02-13 | 14 | 7.143e-06% | 1e-06
4.4 | ECG(chest) - with 3 electrodes |  |  | 2026-02-13 | 2026-02-26 | 14 | 7.143e-06% | 1e-06
5 | Hardware tasks | Parry | Jishiv
5.1 | Node PCB |  |  | 2025-11-17 | 2026-02-14 | 90 | 1.111% | 1
5.2 | Temperature sensor PCB |  |  | 2026-01-31 | 2026-02-13 | 14 | 7.143e-06% | 1e-06
5.3 | PPG sensor PCB |  |  | 2026-02-13 | 2026-02-26 | 14 | 7.143e-06% | 1e-06
5.4 | 1 Lead ECG PCB |  |  | 2026-02-26 | 2026-03-11 | 14 | 0% | 0
6 | Testing | Akash | everyone
6.1 | Test sensors |  |  | 2026-03-16 | 2026-03-29 | 14 | 7.143e-06% | 1e-06
6.1.1 | Compare ECG, Respiratory rate, and Temperature with reference to medical grade equipment |  |  | 2026-03-17 | 2026-03-30 | 14 | 7.143e-06% | 1e-06
6.1.2 | Test vital signs in varying conditions such as movement, and varying external environments |  |  | 2026-03-18 | 2026-03-31 | 14 | 7.143e-06% | 1e-06
6.1.3 | Collect data spanning several days and interpolating results from it |  |  | 2026-03-19 | 2026-04-01 | 14 | 7.143e-06% | 1e-06
7 | Documentation, and Presentation | Ryan | everyone
7.1 | Poster |  |  | 2026-03-16 | 2026-04-14 | 30 | 3.333e-06% | 1e-06
7.2 | Practice presentation |  |  | 2026-04-14 | 2026-04-28 | 15 | 6.667e-06% | 1e-06
7.3 | Final documentation of project |  |  | 2026-03-16 | 2026-04-29 | 45 | 2.222e-06% | 1e-06
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
1.1 | . [ Level 2 Task ] |  |  |  | - |  |  | -
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
1.1.2 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
1.1.2.1 | . . . [ Level 4 Task ]
► Watch How to Create a Gantt Chart in Excel
d
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.